## Sheet1
Student Activities Management System (SAMS)
Tasks | Start date | Days needed | Completion | Adjusted length | Depends on
Requirements Gathering | 2026-01-04 | 10 | 2026-01-16 | 12 | None
System Analysis | 2026-01-18 | 10 | 2026-01-30 | 12 | Requirements Gathering
System Design | 2026-02-01 | 11 | 2026-02-16 | 15 | System Analysis
System Development | 2026-02-16 | 16 | 2026-03-10 | 22 | System Design
System Testing | 2026-03-10 | 7 | 2026-03-19 | 9 | System Development
User Acceptance Testing | 2026-03-19 | 5 | 2026-03-26 | 7 | System Testing
Deployment | 2026-03-26 | 6 | 2026-04-03 | 8 | User Acceptance Testing
Documentation & Training | 2026-04-05 | 15 | 2026-04-24 | 19 | Deployment