## Sheet1
System Analysis and Design Project
Tasks | Start date | Days needed | Completion date | Depends on
Project Planning | 2026-06-15 | 2 | 2026-06-17 | None
Tasks Assigning | 2026-06-18 | 4 | 2026-06-22 | Project Planning
Creating Gantt Chart | 2026-06-23 | 5 | 2026-06-28 | Tasks assigning
Drawing low-fidelity prototypes | 2026-06-29 | 6 | 2026-07-05 | Creating Gantt Chart
DFDs development | 2026-07-06 | 9 | 2026-07-15 | Drawing low-fidelity prototypes
Use Case Model development | 2026-07-16 | 3 | 2026-07-19 | DFDs development
UML Activity Diagrams | 2026-07-20 | 2 | 2026-07-22 | Use Case Model development
UML Class Diagram | 2026-07-23 | 2 | 2026-07-25 | UML Activity Diagrams
Relational database designing | 2026-07-26 | 1 | 2026-07-27 | UML Class Diagram
Submitting phase 1 | 2026-07-28 | 1 | 2026-07-29 | relational database designing
Finalising the project | 2026-08-01 | 5 | 2026-08-06 | Submitting phase 1
Submitting phase 2 (finale) | 2026-08-07 | 2 | 2026-08-09 | Finalising the project