## Sheet1
Student Activities Management System (SAMS)
Tasks | Start date | Days needed | Completion | Depends on
Requirements Gathering | 2026-04-01 | 10 | 15/1/2026 | None
System Analysis | 18/1/2026 | 10 | 29/1/2026 | Requirements Gathering
System Design | 2026-01-02 | 11 | 15/2/2026 | System Analysis
System Development | 16/2/2026 | 16 | 2026-09-03 | System Design
System Testing | 2026-10-03 | 7 | 18/3/2026 | System Development
User Acceptance Testing | 19/3/2026 | 5 | 25/3/2026 | System Testing
Deployment | 26/3/2026 | 6 | 2026-02-04 | User Acceptance Testing
Documentation & Training | 2026-05-04 | 15 | 23/4/2026 | Deployment